## Agile Project Plan
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | Sprint 1
MyChat Application | Aditee, Shasheen | 2020-02-13 | 2020-05-01 |  |  |  | 02/13- 02/27
TASK NAME | Milestone Title | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1 | Research based on how to develop a secure chatapp. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-13 | 2020-02-20 | 7 | Completed
Task 1 | Setting up the framework for the app and installing the dependencies | Shasheen Bandodkar, Aditee Varhadi | 2020-02-13 | 2020-02-13 | 1 | Complete | Started to do research on best viable route to implement MyChat application. Using javascript and React.js framework for development.
Task 2 | Developing a GUI for logging into the chat application. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-14 | 2020-02-15 | 2 | Complete | A Sign Up page.
Task 3 | Settiing up the backend with node.js. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-16 | 2020-02-16 | 1 | Completed
Task 4 | Establishing client and server side connection. | Shasheen Bandodkar, Aditee Varhadi |  |  | 2
Task 5 | Created 'Log in' Page for users. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-17 | 2020-02-18 | 2 | Completed
Task 6 | Accounted event handling in the user login page. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-19 | 2020-02-19 | 1 | Near Completion | When user logs in a particular room, the client side establishes connection with the server side with the username but not the room number yet
Task 7 | Designing GUI / UI for the chat page element of the application. | Shasheen Bandodkar, Aditee Varhadi | 2020-02-20 | 2020-02-20 | 1 | Ongoing